## Sheet1
Date : 2-2-2024
QP Module Testing Report |  |  |  |  | SP Commented
Sr No | Problem Statement | Issue occurred date | Issue resolved Date | Status
1 | The Question Bank (QB) has been successfully created, questions have been added, and it has been assigned to the respective subject. However, when attempting to select the QB format, an error is encountered: 'Please add question banks related to demo test sub100-Theory course.' I kindly request assistance in resolving this issue. | 2024-02-02 |  | Done |  | Soham | Done on my local
2 | The displayed sample format for QB 'format A' appears to be incorrect. Instead of presenting a sample Question Paper (QP), the system should display the sample QP skeleton. | 2024-02-02 |  | Pending | I will give API to backend Team. | Sushant will give sample pdf of respective formats
3 | Issue: When attempting to edit the Question Bank (QB) name, I noticed that after selecting the "Edit QB" option and modifying the QB name, I am prompted to select the course again. Expected: While editing the Question Bank (QB) name, the system should not require the user to reselect the course. The user should only need to modify the QB name without additional steps involving course selection. | 2024-01-04 |  | Done |  | Soham | Done on my local
4 | While bulk uploading questions in QB, if a question contains a comma or inverted comma, the system replaces the comma with a question mark. Is there any solution to address this? | 2024-01-04 |  | Done |  | Soham | Done on my local
5 | An error is occurring when switching from one format of Question Bank (QB) to another, displaying the message 'Insufficient parameters passed.' Please investigate and address this issue. | 2024-01-04 |  | DONE | API issue, Given to Backend team | Soham
6 | To improve user understanding of the QB format, consider adding a preview option. During a discussion with Gauri Mam, she mentioned that such an option existed in our system. I kindly request you to incorporate this feature to enhance the user experience. | 2024-01-04 |  | Pending
7 | After the Question Paper (QP) is approved, questions in the Question Bank (QB) that are already included in the QP cannot be edited by regular users. However, users can add new questions to the QB. If a user attempts to edit or modify a question in the QB that is already part of the approved QP, they will receive a warning message indicating that the question is already included in the QP. Administrators, on the other hand, have the authority to edit or modify questions in the QB even if they are part of the approved QP. However, when an admin attempts to edit or modify a question in the QB that is part of the approved QP, they will also receive a warning message. Despite the warning, admins have the capability to proceed with the edits or modifications. | 2024-06-02 |  | DONE |  | Shreyas
Date : 23-02-2024
QP Module Testing Report
Sr No | Problem Statement | Issue occurred date | Issue resolved Date | Status
1 | When attempting to delete a generated QP, the message "You do not have permission to delete Question Paper Instance!! Please contact ADMIN to delete it." is displayed on the window. | 23-02-2023 |  | Not Solved
2 | When giving approval to a generated QP, instead of displaying '0' in the 'Is Approved' column, it should display 'Yes'. | 23-02-2023 |  | Not Solved
3 | Once a generated QP is approved, it cannot be disapproved. Expected : 1) When the institute admin attempts to remove approval, a warning message should appear on the screen stating: "QP is already approved. You cannot disapprove it. Please contact the admin if you wish to remove approval." 2) Only the admin has the authority to disapprove QP. When the admin tries to remove approval, a warning message should appear on the screen stating: "You are about to remove approval for the QP. Are you sure you want to proceed?" | 23-02-2023 |  | Not Solved
4 | In the last section (Q.4), I configured a total of 15 questions, out of which only 3 are compulsory. However, in the generated QP, more than the total number of questions are asked. | 23-02-2023 |  | Not Solved
5 | When a generated QP is approved, users, faculty, or institute admins attempting to edit or delete a section or section configuration will receive a warning message on the screen. "The QP has been approved. You cannot edit or delete sections or section configurations. Please contact the admin to make any changes." Only the admin has the authority to perform these actions. If the admin attempts to edit or remove the sections and section configuration, a warning message will be displayed on the screen, stating: "Caution: This QP has already been approved. Editing or deleting sections or section configurations may affect the integrity of the approved QP. Are you sure you want to proceed??" | 23-02-2023 |  | Not Solved
6 | When the QP is approved and the admin attempts to delete a section, the system should display a message that accurately reflects the section being removed. Instead of "are you want to remove solve any 3?", it should say "are you sure you want to remove the section Q.1?" to provide clear information to the user. | 23-02-2023 |  | Not Solved
7

## Sheet2
Date : 23-02-2024
QP Module Testing Report
Sr No | Problem Statement | Issue occurred date | Issue resolved Date | Status
1 | When attempting to delete a generated QP, the message "You do not have permission to delete Question Paper Instance!! Please contact ADMIN to delete it." is displayed on the window. | 23-02-2023 |  | Not Working | If QPI is not approved, then Admin can delete QPI now
2 | When giving approval to a generated QP, instead of displaying '0' in the 'Is Approved' column, it should display 'Yes'. | 23-02-2023 |  | Not Working | In DB table ASMT_QP_INSTANCES, on clcik of approve from UI sttaus is inserted as 0, it shall be 'Y'
3 | Once a generated QP is approved, it cannot be disapproved. Expected : 1) When the institute admin attempts to remove approval, a warning message should appear on the screen stating: "QP is already approved. You cannot disapprove it. Please contact the admin if you wish to remove approval." 2) Only the admin has the authority to disapprove QP. When the admin tries to remove approval, a warning message should appear on the screen stating: "You are about to remove approval for the QP. Are you sure you want to proceed?" | 23-02-2023 |  | Not Working
4 | In the last section (Q.4), I configured a total of 15 questions, out of which only 3 are compulsory. However, in the generated QP, more than the total number of questions are asked. | 23-02-2023 |  | Not Working
5 | When a generated QP is approved, users, faculty, or institute admins attempting to edit or delete a section or section configuration will receive a warning message on the screen. "The QP has been approved. You cannot edit or delete sections or section configurations. Please contact the admin to make any changes." Only the admin has the authority to perform these actions. If the admin attempts to edit or remove the sections and section configuration, a warning message will be displayed on the screen, stating: "Caution: This QP has already been approved. Editing or deleting sections or section configurations may affect the integrity of the approved QP. Are you sure you want to proceed??" | 23-02-2023 |  | Not Working
6 | When the QP is approved and the admin attempts to delete a section, the system should display a message that accurately reflects the section being removed. Instead of "are you want to remove solve any 3?", it should say "are you sure you want to remove the section Q.1?" to provide clear information to the user. Note: When attempting to delete the section, the section does not get deleted. Instead, the spinner continues to rotate indefinitely. | 23-02-2023 |  | Not Working
7 | When the admin attempts to delete a pattern, the system should display a message that ensures clarity and confirmation. Instead of "do you want to completely remove?", it should say "are you sure you want to delete the pattern?" to accurately reflect the action being taken and prompt the user for confirmation. Note: When attempting to delete the pattern, the pattern does not get deleted. Instead, the spinner continues to rotate indefinitely. | 23-02-2023 |  | Not Working
8 | When a generated QP is approved, users, faculty, or institute admins attempting to edit or delete a pattern will receive a warning message on the screen. "The QP has been approved. You cannot edit or delete pattern. Please contact the admin to make any changes." Only the admin has the authority to perform these actions. If the admin attempts to edit or remove the pattern, a warning message will be displayed on the screen, stating: "Caution: This QP has already been approved. Editing or deleting pattern may affect the integrity of the approved QP. Are you sure you want to proceed??" | 23-02-2023 |  | Not Working
9 | Once the generated QP is approved, users are unable to edit or delete questions that have already been included in the QP. They can only add new questions to the QB. If a user attempts to edit or delete a question, a warning message will appear on the screen stating: "This question has already been included in the generated QP. You cannot edit or delete the question." | 23-02-2023 |  | Not Working